## WP Table
Partner | WP1 | WP2 | WP3 | WP4 | WP5 | total | % | Name | WP title | Lead no. | Lead participant | Person months | Start month | End month
SIL | 20 | 18 | 60 | 40 | 30 | 168 | 49.7% | WP1 | Project management | 1 | SIL | 30 | 1 | 30
SYNC | 5 | 10 | 30 | 20 | 20 | 85 | 25.15% | WP2 | System blue-print | 1 | SIL | 38 | 1 | 6
EXUS | 5 | 10 | 30 | 20 | 20 | 85 | 25.15% | WP3 | System delivery | 1 | SIL | 120 | 1 | 30
total (PM) | 30 | 38 | 120 | 80 | 70 | 338 | 100% | WP4 | Piloting | 2 | SYNC | 80 | 2 | 30
% | 8.876% | 11.24% | 35.5% | 23.67% | 20.71% | 100% |  | WP5 | Go-to-market | 3 | EXUS | 70 | 1 | 30
338
WP2+WP3 | 158 | 46.75%
WP4+WP5 | 150 | 44.38% | [5 empty] | Total amount other costs | 167000 | 82000 | 82000
[8 empty] | Description | SIL | SYNC | EXUS | Details in part B
[8 empty] | Audit costs (€) | 7000 | 7000 | 7000 | EU requirements
[8 empty] | Dissemination costs (exhibits) | 35000 | 35000 | 35000 | Section 2.1
[8 empty] | SME pilot support | 80000 |  |  | 20 SME piloting (€4000 each)
[8 empty] | External cloud costs | 10000 | 5000 | 5000 | SGX-enabled hosts
[8 empty] | Travel costs (see details below) | 35000 | 35000 | 35000
[8 empty] | Conferences | 4 | 4 | 4
[8 empty] | Project meetings | 5 | 5 | 5
[8 empty] | Reviews | 2 | 2 | 2
[8 empty] | Roadshow meetings | 20 | 20 | 20
[8 empty] | Piloting sessions | 20 | 20 | 20
[11 empty] | Partner |  | Financial Information
[12 empty] | Cost | % | Funding | %
| SIL | SYNC | EXUS | [7 empty] | SIL | 1678750 | 49.81% | 1175125 | 49.81%
PM rate | 7000 | 4500 | 7000 | [7 empty] | SYNC | 845000 | 25.07% | 591500 | 25.07%
RTD PMs | 168 | 132 | 85 | [7 empty] | EXUS | 846250 | 25.11% | 592375 | 25.11%
MGT PMs | 0 | 0 | 0 | [7 empty] | Total | 3370000 |  | 2359000
Personnel Costs | 1176000 | 594000 | 595000
Other Costs | 167000 | 82000 | 82000
Subcontracting | 0 | 0 | 0
OH rate | 25% | 25% | 25%
Indirect Costs | 335750 | 169000 | 169250
Total Costs | 1678750 | 845000 | 846250
EC Requested Contribution | 1175125 | 591500 | 592375
Total costs | 3370000
Other costs: | 331000
% | 9.822%

## Other Costs
Total amount other costs | 167000 | 82000 | 82000
Description | SIL | SYNC | EXUS | Details in part B
Audit costs (€) | 7000 | 7000 | 7000 | EU requirements
Dissemination costs (exhibits) | 35000 | 35000 | 35000 | Section 2.1
SME pilot support | 80000 |  |  | 20 SME piloting (€4000 each)
External cloud costs | 10000 | 5000 | 5000 | SGX-enabled hosts
Travel costs (see details below) | 35000 | 35000 | 35000
Conferences | 4 | 4 | 4
Project meetings | 5 | 5 | 5
Reviews | 2 | 2 | 2
Roadshow meetings | 20 | 20 | 20
Piloting sessions | 20 | 20 | 20