## Feuil1
| Project Month | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
WP1 | Project Management | 6: D1.1; 12: D1.2; 24: D1.3
Task T1.1: Administrative management
Task T1.2: Delivery coordination
Task T1.3: IPR and licensing management
WP2 | System Blueprint | 6: D2.1; 12: D2.2; 24: D2.3
Task T2.1: System requirements
Task T2.2: Secure Docker image generation
Task T2.3: Secure Docker client API extensions
Task T2.4: Secure key service and management
Task T2.5: Secure development support
WP3 | Language and security mechanisms | 6: D3.1; 12: D3.2; 24: D3.3
Task T3.1: Language and security requirements
Task T3.2: Secure client- and server-side language support
Task T3.3: APIs and language abstractions for secure enclaves
Task T3.4: Security policy definition and enforcement
Task T3.5: Security assessment and analysis tools
WP4 | Client-side security | 6: D4.1; 12: D4.2; 24: D4.3
Task T4.1: Client-side security requirements
Task T4.2: Browser support for client-side trusted computing
Task T4.3: Support for secure communication and attestation
Task T4.4: Mobile device integration
WP5 | Application use cases | 6: D5.1; 18: D5.2; 24: D5.3
Task T5.1: Application requirements
Task T5.2: Secure Edge-based IoT
Task T5.3: Trustworthy Credit Scoring
Task T5.4: Secure DBMS
Task T5.5: Efficient Blockchain
WP6 | Dissemination, Exploitation, and Communication | 3: D6.1; 12: D6.2; 24: D6.3, D6.4
Task T6.1: Dissemination and clustering activities
Task T6.2: Exploitation
Task T6.3: Communication activities
WP7 | Project Management | 3: D7.1
Task T7.1: Internal consortium communication strategy definition
Task T7.2: Establishing project management and quality assurance procedures
Task T7.3: Technical management
Task T7.4: Administrative, financial and legal management
| Milestones | 6: M1; 12: M2; 24: M3